## Baseline Schedule (hidden)
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Commercial IT Project | 1 |  |  | 2010-10-19 08:00 | 2011-01-05 14:00 | 56d 5h |  |  | 20300 |  |  | 33622.8 | 78.25
22 | Explore the market | 1.1 |  | FS23 | 2010-10-19 08:00 | 2010-11-01 17:00 | 10d |  | 0 | 4000 | 0 | 0 | 4000 | 13.375
23 | Set up a survey | 1.2 | 22FS | FS24 | 2010-11-02 08:00 | 2010-11-04 17:00 | 3d |  | 0 | 2000 | 0 | 0 | 2000 | 2.375
24 | Analysis of the market | 1.3 | 23FS | FS1 | 2010-11-05 08:00 | 2010-11-25 17:00 | 15d |  | 0 | 1000 | 0 | 0 | 1000 | 20.375
1 | Problem study/analysis | 1.4 | 24FS | FS2;FS3;FS39;FS40 | 2010-11-26 08:00 | 2010-11-30 17:00 | 3d | Analyst programmer;IT Manager[0.20 #1] | 595.2 | 0 | 0 | 0 | 595.2 | 4.375
39 | Negotiate and buy server | 1.5 | 1FS | FS41 | 2010-12-01 08:00 | 2010-12-02 17:00 | 2d | Marketing manager[0.50 #1];IT Manager[0.10 #1] | 286.4 | 10000 | 0 | 0 | 10286.4 | 1.375
40 | Negotiate and buy computer | 1.6 | 1FS | FS42 | 2010-12-01 08:00 | 2010-12-02 17:00 | 2d | IT Manager[0.10 #1];Marketing manager[0.50 #1] | 286.4 | 3000 | 0 | 0 | 3286.4 | 1.375
2 | Processmodels (BPMN) | 1.7 | 1FS | FS4;FS7 | 2010-12-01 08:00 | 2010-12-01 16:00 | 7h | Analyst programmer | 133 | 0 | 0 | 0 | 133 | 0.33333
3 | Conceptual datamodel (ER) | 1.8 | 1FS | FS4;FS7 | 2010-12-01 08:00 | 2010-12-01 17:00 | 1d | Analyst programmer | 152 | 0 | 0 | 0 | 152 | 0.375
4 | Normalisation DB | 1.9 | 2FS;3FS | FS5 | 2010-12-02 08:00 | 2010-12-02 12:00 | 4h | Database administrator | 76 | 0 | 0 | 0 | 76 | 0.16667
5 | Datamap | 1.10 | 4FS | FS6 | 2010-12-02 13:00 | 2010-12-02 14:00 | 1h | Analyst programmer[0.50 #1];Database administrator[0.50 #1] | 19 | 0 | 0 | 0 | 19 | 0.041667
6 | Logic Databasemodel | 1.11 | 5FS | FS8;FS9 | 2010-12-02 14:00 | 2010-12-02 16:00 | 2h | Database administrator | 38 | 0 | 0 | 0 | 38 | 0.083333
7 | Software design (UML-class diagram) | 1.12 | 2FS;3FS | FS10;FS11 | 2010-12-02 08:00 | 2010-12-03 17:00 | 2d | Analyst programmer[0.30 #1] | 91.2 | 0 | 0 | 0 | 91.2 | 1.375
8 | Develop Database Tables 1 | 1.13 | 6FS | FS12 | 2010-12-02 16:00 | 2010-12-03 14:00 | 6h | Database administrator | 114 | 0 | 0 | 0 | 114 | 0.91667
9 | Develop Database Tables 2 | 1.14 | 6FS | FS13 | 2010-12-02 16:00 | 2010-12-03 16:00 | 1d | Database administrator | 152 | 0 | 0 | 0 | 152 | 1
10 | Design & Develop GUI 1 | 1.15 | 7FS | FS18;FS25;FS26 | 2010-12-06 08:00 | 2010-12-07 17:00 | 2d | Programmers | 272 | 0 | 0 | 0 | 272 | 1.375
11 | Design & Develop GUI 2 | 1.16 | 7FS | FS19;FS25;FS26 | 2010-12-06 08:00 | 2010-12-08 14:00 | 2d 5h | Programmers[1.50 #3] | 535.5 | 0 | 0 | 0 | 535.5 | 2.25
25 | Design CD-box | 1.17 | 10FS;11FS |  | 2010-12-08 14:00 | 2010-12-22 14:00 | 10d |  | 0 | 250 | 0 | 0 | 250 | 14
26 | Design CD-labels | 1.18 | 10FS;11FS |  | 2010-12-08 14:00 | 2010-12-22 14:00 | 10d |  | 0 | 50 | 0 | 0 | 50 | 14
12 | Develop SQL's 1 | 1.19 | 8FS | FS14 | 2010-12-03 14:00 | 2010-12-07 16:00 | 2d 2h | Database administrator[0.40 #1] | 136.8 | 0 | 0 | 0 | 136.8 | 4.0833
13 | Develop SQL's 2 | 1.20 | 9FS | FS15 | 2010-12-03 16:00 | 2010-12-08 11:00 | 2d 4h | Database administrator[0.60 #1] | 228 | 0 | 0 | 0 | 228 | 4.7917
14 | Debug SQL’s 1 | 1.21 | 12FS | FS16 | 2010-12-07 16:00 | 2010-12-09 09:00 | 1d 2h | Database administrator[0.40 #1] | 76 | 0 | 0 | 0 | 76 | 1.7083
15 | Debug SQL’s 2 | 1.22 | 13FS | FS17 | 2010-12-08 11:00 | 2010-12-09 16:00 | 1d 4h | Database administrator[0.60 #1] | 136.8 | 0 | 0 | 0 | 136.8 | 1.2083
16 | Implement SQL’s in JAVA 1 | 1.23 | 14FS | FS18 | 2010-12-09 09:00 | 2010-12-09 10:00 | 1h | Programmers[2.00 #3] | 34 | 0 | 0 | 0 | 34 | 0.041667
17 | Implement SQL’s in JAVA 2 | 1.24 | 15FS | FS19 | 2010-12-09 16:00 | 2010-12-09 17:00 | 1h | Programmers[2.50 #3] | 42.5 | 0 | 0 | 0 | 42.5 | 0.041667
18 | Develop program 1 | 1.25 | 16FS;10FS | FS20 | 2010-12-09 10:00 | 2010-12-14 10:00 | 3d | Programmers[2.00 #3] | 816 | 0 | 0 | 0 | 816 | 5
19 | Develop program 2 | 1.26 | 17FS;11FS | FS21 | 2010-12-10 08:00 | 2010-12-15 14:00 | 3d 5h | Programmers[3.00 #3] | 1479 | 0 | 0 | 0 | 1479 | 5.25
20 | Testing & Debugging 1 | 1.27 | 18FS | FS27;FS37;FS38 | 2010-12-14 10:00 | 2010-12-15 10:00 | 1d | Programmers[2.00 #3] | 272 | 0 | 0 | 0 | 272 | 1
21 | Testing & Debugging 2 | 1.28 | 19FS | FS27;FS37;FS38 | 2010-12-15 14:00 | 2010-12-16 14:00 | 1d | Programmers[3.00 #3] | 408 | 0 | 0 | 0 | 408 | 1
38 | Visitations by sales representatives | 1.29 | 20FS;21FS |  | 2010-12-16 14:00 | 2010-12-30 14:00 | 10d | Sales representatives[2.00 #2] | 2400 | 0 | 0 | 0 | 2400 | 14
37 | Direct mailings | 1.30 | 20FS;21FS |  | 2010-12-16 14:00 | 2010-12-16 16:00 | 2h | Secretary;Marketing manager[0.50 #1] | 52 | 0 | 0 | 0 | 52 | 0.083333
27 | Make up report + presentation Alpha version | 1.31 | 20FS;21FS | FS28 | 2010-12-16 14:00 | 2010-12-20 14:00 | 2d | Secretary;Analyst programmer[0.30 #1] | 267.2 | 0 | 0 | 0 | 267.2 | 4
28 | Presentation Alpha version | 1.32 | 27FS | FS29 | 2010-12-20 14:00 | 2010-12-20 16:00 | 2h | IT Manager;Analyst programmer | 96 | 0 | 0 | 0 | 96 | 0.083333
29 | Reading of management report + Approval Alpha | 1.33 | 28FS | FS31 | 2010-12-20 16:00 | 2010-12-21 12:00 | 5h | IT Manager[0.50 #1] | 72.5 | 0 | 0 | 0 | 72.5 | 0.83333
31 | Testing phase Alpha version | 1.34 | 29FS | FS32 | 2010-12-21 13:00 | 2010-12-24 12:00 | 3d | Programmers[2.00 #3];Database administrator[0.30 #1];Analyst programmer[0.10 #1] | 998.4 | 0 | 0 | 0 | 998.4 | 2.9583
32 | Fix outstanding problems from Alpha | 1.35 | 31FS | FS33 | 2010-12-24 13:00 | 2010-12-27 15:00 | 1d 2h | Programmers | 170 | 0 | 0 | 0 | 170 | 3.0833
33 | Make up Report+ presentation Beta version | 1.36 | 32FS | FS34 | 2010-12-27 15:00 | 2010-12-28 15:00 | 1d | Secretary;Analyst programmer[0.20 #1] | 118.4 | 0 | 0 | 0 | 118.4 | 1
34 | Presentation Beta version | 1.37 | 33FS | FS35 | 2010-12-28 15:00 | 2010-12-28 17:00 | 2h | IT Manager;Analyst programmer | 96 | 0 | 0 | 0 | 96 | 0.083333
35 | Reading of management report + Approval Beta | 1.38 | 34FS | FS36;FS41;FS42 | 2010-12-29 08:00 | 2010-12-29 14:00 | 5h | IT Manager[0.50 #1] | 72.5 | 0 | 0 | 0 | 72.5 | 0.25
36 | Launch and installation Beta version | 1.39 | 35FS |  | 2010-12-29 14:00 | 2011-01-05 14:00 | 5d | Technicians[3.00 #3] | 1560 | 0 | 0 | 0 | 1560 | 7
41 | Installation server | 1.40 | 35FS;39FS |  | 2010-12-29 14:00 | 2011-01-05 14:00 | 5d | Technicians | 520 | 0 | 0 | 0 | 520 | 7
42 | Installation computer | 1.41 | 35FS;40FS |  | 2010-12-29 14:00 | 2011-01-05 14:00 | 5d | Technicians | 520 | 0 | 0 | 0 | 520 | 7

## Estimate & Overview
Pricing Model | Region | Portfolio | ID | Project Name | Baseline Start | Baseline End | Duration |  | Resource Cost | Assets Cost | Project Bid Value | Total Cost | Estimated Profit | Estimated Profit % | Project Billed Value | Actual Profit | Actual Profit % | Strategic Allignment | Project Health | Accrual Cost
Fixed Price | EMEA | IMS | 1 | Project Signal | 2019-10-06 08:00 | 2021-02-06 17:00 | 17m | 17 | 272 | 0 | 272502.4038 | 197465.51 | 75036.8938 | 38% | 275977.9932 | 78512.4832 | 39.76% | Systems & Data Reliability | Green | 3159.6368
Fixed Price | APAC | R & D | 7 | Project Force | 2020-06-02 16:00 | 2021-08-02 14:00 | 15m | 15 | 114 | 0 | 246512.6006 | 185347.82 | 61164.7806 | 33% | 246512.6 | 61164.78 | 33% | Technology Modernization | Green | 0
T & M | Americas | Client Based | 6 | Project Point | 2020-05-05 08:00 | 2021-05-05 17:00 | 13m | 13 | 0 | 1000 | 91000 | 176564.43 | -85564.43 | -48.46% | 91000 | -85564.43 | -48.46% | Growth & Innovation | Red | 0
Fixed Price | EMEA | Client Based | 2 | Quest Program | 2019-12-05 16:00 | 2021-06-05 16:00 | 19m | 19 | 152 | 0 | 338729.9666 | 238542.23 | 100187.7366 | 42% | 338729.9666 | 100187.7366 | 42% | Growth & Innovation | Green | 0
Fixed Price | APAC | Client Based | 3 | Dynamic Program | 2020-03-01 08:00 | 2021-03-01 16:00 | 14m | 14 | 133 | 0 | 130655.44 | 109543.54 | 21111.9 | 19.27% | 130655.44 | 21111.9 | 19.27% | Growth & Innovation | Red | 0
Fixed Price | Americas | IMS | 13 | Project Illuminate | 2021-01-02 08:00 | 2021-10-02 12:00 | 10m | 10 | 76 | 0 | 89878.329 | 66576.54 | 23301.789 | 35% | 101998.31 | 35421.77 | 53.2% | Systems & Data Reliability | Green | 12120.01
Fixed Price | EMEA | Client Based | 11 | Magnetic Program | 2020-12-03 13:00 | 2021-12-03 14:00 | 13m | 13 | 19 | 0 | 272394.248 | 194567.32 | 77826.928 | 40% | 272394.2 | 77826.88 | 40% | Growth & Innovation | Green | 0
Fixed Price | APAC | IMS | 10 | Project Mecha | 2020-10-26 08:00 | 2021-09-26 17:00 | 12m | 12 | 595.2 | 0 | 135310.721 | 104085.17 | 31225.551 | 30% | 135310.8 | 31225.63 | 30% | Systems & Data Reliability | Amber | 0
Fixed Price | Americas | Client Based | 9 | Project Systems | 2020-08-09 14:00 | 2021-09-09 16:00 | 14m | 14 | 38 | 0 | 220619.3085 | 163421.71 | 57197.5985 | 35% | 220618.3 | 57196.59 | 35% | Growth & Innovation | Green | 0
Fixed Price | EMEA | R & D | 4 | Program Pad | 2020-04-01 08:00 | 2021-09-01 17:00 | 18m | 18 | 286.4 | 10000 | 241594.568 | 176346.4 | 65248.168 | 37% | 241594.56 | 65248.16 | 37% | Technology Modernization | Green | 0
Fixed Price | APAC | Client Based | 8 | Command Program | 2020-07-11 | 2021-03-11 17:00 | 9m | 9 | 0 | 2000 | 60355.2444 | 45723.67 | 14631.5744 | 32% | 61882.24 | 16158.57 | 35.34% | Growth & Innovation | Green | 1527
Fixed Price | Americas | R & D | 12 | Project Zen | 2020-12-17 08:00 | 2021-05-17 17:00 | 6m | 6 | 152 | 0 | 37914.9 | 26890 | 11024.9 | 41% | 37914.9 | 11024.9 | 41% | Technology Modernization | Green | 0
Fixed Price | EMEA | Client Based | 14 | Project Synergy | 2021-02-12 08:00 | 2021-10-12 17:00 | 9m | 9 | 286.4 | 3000 | 70836.956 | 52863.4 | 17973.556 | 34% | 70836.956 | 17973.556 | 34% | Growth & Innovation | Green | 0
Fixed Price | APAC | IMS | 5 | Project Breeze | 2020-04-19 08:00 | 2020-11-19 17:00 | 8m | 8 | 0 | 4000 | 43709.64 | 33622.8 | 10086.84 | 30% | 43709.64 | 10086.84 | 30% | Systems & Data Reliability | Amber | 0
Fixed Price | Americas | Client Based | 15 | Native Program | 2021-03-07 08:00 | 2021-11-07 17:00 | 9m | 9 | 91.2 | 0 | 118790.5328 | 87345.98 | 31444.5528 | 36% | 118790.5328 | 31444.5528 | 36% | Growth & Innovation | Green | 0

## Additional Col (hidden)
Project Name | Strategic Allignment | Project Health
Project Signal | Systems & Data Reliability | Green
Project Force | Technology Modernization | Green
Project Point | Growth & Innovation | Red
Quest Program | Growth & Innovation | Green
Dynamic Program | Growth & Innovation | Red
Project Illuminate | Systems & Data Reliability | Green
Magnetic Program | Growth & Innovation | Green
Project Mecha | Systems & Data Reliability | Amber
Project Systems | Growth & Innovation | Green | Strategic Allignment
Program Pad | Technology Modernization | Green
Command Program | Growth & Innovation | Green
Project Zen | Technology Modernization | Green
Project Synergy | Growth & Innovation | Green
Project Breeze | Systems & Data Reliability | Amber
Native Program | Growth & Innovation | Green

## 1. Project Signal
ID | Project Name | Month | Actual Cost | Estimate | Billing | Accrual Monthly | Actual Profit
1 | Project Signal | 2019-10-01 | 8689 | 16029.55 | 16029.5532 | 0 | 7340.5532
1 | Project Signal | 2019-11-01 | 9734.21 | 16029.55 | 16029.55 | 0 | 6295.34
1 | Project Signal | 2019-12-01 | 11340.77 | 16029.55 | 16345.55 | 0 | 5004.78
1 | Project Signal | 2020-01-01 | 10876.58 | 16029.55 | 16029.55 | 0 | 5152.97
1 | Project Signal | 2020-02-01 | 15917.12 | 16029.55 | 18451.16 | 2421.6068 | 2534.04
1 | Project Signal | 2020-03-01 | 13765.54 | 16029.55 | 16029.55 | 0 | 2264.01
1 | Project Signal | 2020-04-01 | 13234.89 | 16029.55 | 16029.55 | 0 | 2794.66
1 | Project Signal | 2020-05-01 | 13340 | 16029.55 | 16029.55 | 0 | 2689.55
1 | Project Signal | 2020-06-01 | 14345.65 | 16029.55 | 16767.58 | 738.03 | 2421.93
1 | Project Signal | 2020-07-01 | 11615.67 | 16029.55 | 16029.55 | 0 | 4413.88
1 | Project Signal | 2020-08-01 | 11369.34 | 16029.55 | 16029.55 | 0 | 4660.21
1 | Project Signal | 2020-09-01 | 11432.93 | 16029.55 | 16029.55 | 0 | 4596.62
1 | Project Signal | 2020-10-01 | 11584.71 | 16029.55 | 16029.55 | 0 | 4444.84
1 | Project Signal | 2020-11-01 | 9721.52 | 16029.55 | 16029.55 | 0 | 6308.03
1 | Project Signal | 2020-12-01 | 10086.78 | 16029.55 | 16029.55 | 0 | 5942.77
1 | Project Signal | 2021-01-01 | 10451.59 | 16029.55 | 16029.55 | 0 | 5577.96
1 | Project Signal | 2021-02-01 | 9959.21 | 16029.55 | 16029.55 | 0 | 6070.34
1 | Project Signal | 2021-03-01 | 0 | 0 | 0 | 0 | 0
1 | Project Signal | 2021-04-01 | 0 | 0 | 0 | 0 | 0
1 | Project Signal | 2021-05-01 | 0 | 0 | 0 | 0 | 0
1 | Project Signal | 2021-06-01 | 0 | 0 | 0 | 0 | 0
1 | Project Signal | 2021-07-01 | 0 | 0 | 0 | 0 | 0
1 | Project Signal | 2021-08-01 | 0 | 0 | 0 | 0 | 0
1 | Project Signal | 2021-09-01 | 0 | 0 | 0 | 0 | 0
1 | Project Signal | 2021-10-01 | 0 | 0 | 0 | 0 | 0
1 | Project Signal | 2021-11-01 | 0 | 0 | 0 | 0 | 0
1 | Project Signal | 2021-12-01 | 0 | 0 | 0 | 0 | 0

## 7. Project Force
ID | Project Name | Month | Actual Cost | Estimate | Billing | Accrual Monthly | Actual Profit
7 | Project Force | 2019-10-01 | 0 | 0 | 0 | 0 | 0
7 | Project Force | 2019-11-01 | 0 | 0 | 0 | 0 | 0
7 | Project Force | 2019-12-01 | 0 | 0 | 0 | 0 | 0
7 | Project Force | 2020-01-01 | 0 | 0 | 0 | 0 | 0
7 | Project Force | 2020-02-01 | 0 | 0 | 0 | 0 | 0
7 | Project Force | 2020-03-01 | 0 | 0 | 0 | 0 | 0
7 | Project Force | 2020-04-01 | 0 | 0 | 0 | 0 | 0
7 | Project Force | 2020-05-01 | 0 | 0 | 0 | 0 | 0
7 | Project Force | 2020-06-01 | 9876.34 | 16434.17 | 16434.17 | 0 | 6557.83
7 | Project Force | 2020-07-01 | 10321.78 | 16434.17 | 16434.17 | 0 | 6112.39
7 | Project Force | 2020-08-01 | 11379.34 | 16434.17 | 16434.17 | 0 | 5054.83
7 | Project Force | 2020-09-01 | 11432.93 | 16434.17 | 16434.17 | 0 | 5001.24
7 | Project Force | 2020-10-01 | 12584.71 | 16434.17 | 16434.17 | 0 | 3849.46
7 | Project Force | 2020-11-01 | 12785.25 | 16434.17 | 16434.17 | 0 | 3648.92
7 | Project Force | 2020-12-01 | 13675.35 | 16434.17 | 16434.17 | 0 | 2758.82
7 | Project Force | 2021-01-01 | 13984.57 | 16434.17 | 16434.17 | 0 | 2449.6
7 | Project Force | 2021-02-01 | 15612.74 | 16434.17 | 16434.17 | 0 | 821.43
7 | Project Force | 2021-03-01 | 14234.95 | 16434.17 | 16434.17 | 0 | 2199.22
7 | Project Force | 2021-04-01 | 13785.62 | 16434.18 | 16434.18 | 0 | 2648.56
7 | Project Force | 2021-05-01 | 12384.31 | 16434.18 | 16434.18 | 0 | 4049.87
7 | Project Force | 2021-06-01 | 12112.15 | 16434.18 | 16434.18 | 0 | 4322.03
7 | Project Force | 2021-07-01 | 11756.47 | 16434.18 | 16434.18 | 0 | 4677.71
7 | Project Force | 2021-08-01 | 9421.31 | 16434.18 | 16434.18 | 0 | 7012.87
7 | Project Force | 2021-09-01 | 0 | 0 | 0 | 0 | 0
7 | Project Force | 2021-10-01 | 0 | 0 | 0 | 0 | 0
7 | Project Force | 2021-11-01 | 0 | 0 | 0 | 0 | 0
7 | Project Force | 2021-12-01 | 0 | 0 | 0 | 0 | 0

## 6. Project Point
ID | Project Name | Month | Actual Cost | Estimate | Billing | Accrual Monthly | Actual Profit
6 | Project Point | 2019-10-01
6 | Project Point | 2019-11-01
6 | Project Point | 2019-12-01
6 | Project Point | 2020-01-01
6 | Project Point | 2020-02-01
6 | Project Point | 2020-03-01
6 | Project Point | 2020-04-01
6 | Project Point | 2020-05-01 | 10561.87 | 7000 | 7000 | 0 | -3561.87
6 | Project Point | 2020-06-01 | 11365.75 | 7000 | 7000 | 0 | -4365.75
6 | Project Point | 2020-07-01 | 11946.23 | 7000 | 7000 | 0 | -4946.23
6 | Project Point | 2020-08-01 | 13324.36 | 7000 | 7000 | 0 | -6324.36
6 | Project Point | 2020-09-01 | 13682.94 | 7000 | 7000 | 0 | -6682.94
6 | Project Point | 2020-10-01 | 14236.51 | 7000 | 7000 | 0 | -7236.51
6 | Project Point | 2020-11-01 | 15231.87 | 7000 | 7000 | 0 | -8231.87
6 | Project Point | 2020-12-01 | 15436.72 | 7000 | 7000 | 0 | -8436.72
6 | Project Point | 2021-01-01 | 15612.74 | 7000 | 7000 | 0 | -8612.74
6 | Project Point | 2021-02-01 | 14760.56 | 7000 | 7000 | 0 | -7760.56
6 | Project Point | 2021-03-01 | 14234.95 | 7000 | 7000 | 0 | -7234.95
6 | Project Point | 2021-04-01 | 13785.62 | 7000 | 7000 | 0 | -6785.62
6 | Project Point | 2021-05-01 | 12384.31 | 7000 | 7000 | 0 | -5384.31
6 | Project Point | 2021-06-01
6 | Project Point | 2021-07-01
6 | Project Point | 2021-08-01
6 | Project Point | 2021-09-01
6 | Project Point | 2021-10-01
6 | Project Point | 2021-11-01
6 | Project Point | 2021-12-01

## 2. Quest Program
ID | Project Name | Month | Actual Cost | Estimate | Billing | Accrual Monthly | Actual Profit
2 | Quest Program | 2019-10-01
2 | Quest Program | 2019-11-01
2 | Quest Program | 2019-12-01 | 9365.41 | 17827.893 | 17827.89 | 0 | 8462.48
2 | Quest Program | 2020-01-01 | 9874.84 | 17827.89 | 17827.89 | 0 | 7953.05
2 | Quest Program | 2020-02-01 | 10340.76 | 17827.89 | 17827.89 | 0 | 7487.13
2 | Quest Program | 2020-03-01 | 11236.32 | 17827.89 | 17827.89 | 0 | 6591.57
2 | Quest Program | 2020-04-01 | 11562.28 | 17827.89 | 17827.89 | 0 | 6265.61
2 | Quest Program | 2020-05-01 | 12102.61 | 17827.89 | 17827.89 | 0 | 5725.28
2 | Quest Program | 2020-06-01 | 11986.32 | 17827.89 | 17827.89 | 0 | 5841.57
2 | Quest Program | 2020-07-01 | 13362.11 | 17827.89 | 17827.89 | 0 | 4465.78
2 | Quest Program | 2020-08-01 | 14562.01 | 17827.89 | 17827.89 | 0 | 3265.88
2 | Quest Program | 2020-09-01 | 15372.68 | 17827.89 | 17827.89 | 0 | 2455.21
2 | Quest Program | 2020-10-01 | 15467.51 | 17827.89 | 17827.89 | 0 | 2360.38
2 | Quest Program | 2020-11-01 | 15231.87 | 17827.89 | 17827.89 | 0 | 2596.02
2 | Quest Program | 2020-12-01 | 15436.72 | 17827.89 | 17827.89 | 0 | 2391.17
2 | Quest Program | 2021-01-01 | 15821.74 | 17827.89 | 17827.89 | 0 | 2006.15
2 | Quest Program | 2021-02-01 | 14760.56 | 17827.9 | 17827.9 | 0 | 3067.34
2 | Quest Program | 2021-03-01 | 14254.95 | 17827.9 | 17827.9 | 0 | 3572.95
2 | Quest Program | 2021-04-01 | 13325.62 | 17827.9 | 17827.9 | 0 | 4502.28
2 | Quest Program | 2021-05-01 | 11384.31 | 17827.9 | 17827.9 | 0 | 6443.59
2 | Quest Program | 2021-06-01 | 3093.61 | 17827.9 | 17827.9 | 0 | 14734.29
2 | Quest Program | 2021-07-01
2 | Quest Program | 2021-08-01
2 | Quest Program | 2021-09-01
2 | Quest Program | 2021-10-01
2 | Quest Program | 2021-11-01
2 | Quest Program | 2021-12-01

## 3. Dynamic Program
ID | Project Name | Month | Actual Cost | Estimate | Billing | Accrual Monthly | Actual Profit
3 | Dynamic Program | 2019-10-01
3 | Dynamic Program | 2019-11-01
3 | Dynamic Program | 2019-12-01
3 | Dynamic Program | 2020-01-01
3 | Dynamic Program | 2020-02-01
3 | Dynamic Program | 2020-03-01 | 4376.44 | 9332.53 | 9332.53 | 0 | 4956.09
3 | Dynamic Program | 2020-04-01 | 4982.5 | 9332.53 | 9332.53 | 0 | 4350.03
3 | Dynamic Program | 2020-05-01 | 6232.77 | 9332.53 | 9332.53 | 0 | 3099.76
3 | Dynamic Program | 2020-06-01 | 6652.18 | 9332.53 | 9332.53 | 0 | 2680.35
3 | Dynamic Program | 2020-07-01 | 12732.56 | 9332.53 | 9332.53 | 0 | -3400.03
3 | Dynamic Program | 2020-08-01 | 9341.4 | 9332.53 | 9332.53 | 0 | -8.87
3 | Dynamic Program | 2020-09-01 | 10521.36 | 9332.53 | 9332.53 | 0 | -1188.83
3 | Dynamic Program | 2020-10-01 | 13672.59 | 9332.53 | 9332.53 | 0 | -4340.06
3 | Dynamic Program | 2020-11-01 | 9817.46 | 9332.53 | 9332.53 | 0 | -484.93
3 | Dynamic Program | 2020-12-01 | 8716.52 | 9332.53 | 9332.53 | 0 | 616.01
3 | Dynamic Program | 2021-01-01 | 6547.55 | 9332.53 | 9332.53 | 0 | 2784.98
3 | Dynamic Program | 2021-02-01 | 5631.24 | 9332.53 | 9332.53 | 0 | 3701.29
3 | Dynamic Program | 2021-03-01 | 5329.66 | 9332.54 | 9332.54 | 0 | 4002.88
3 | Dynamic Program | 2021-04-01 | 4989.31 | 9332.54 | 9332.54 | 0 | 4343.23
3 | Dynamic Program | 2021-05-01
3 | Dynamic Program | 2021-06-01
3 | Dynamic Program | 2021-07-01
3 | Dynamic Program | 2021-08-01
3 | Dynamic Program | 2021-09-01
3 | Dynamic Program | 2021-10-01
3 | Dynamic Program | 2021-11-01
3 | Dynamic Program | 2021-12-01

## 13. Project Illluminate
ID | Project Name | Month | Actual Cost | Estimate | Billing | Accrual Monthly | Actual Profit
13 | Project Illuminate | 2021-01-01 | 0 | 8987.83 | 8987.83 | 0 | 8987.83
13 | Project Illuminate | 2021-02-01 | 1229.55 | 8987.83 | 8987.83 | 0 | 7758.28
13 | Project Illuminate | 2021-03-01 | 2800 | 8987.83 | 8987.83 | 0 | 6187.83
13 | Project Illuminate | 2021-04-01 | 11511 | 8987.83 | 11511 | 2523.17 | 0
13 | Project Illuminate | 2021-05-01 | 11900.84 | 8987.83 | 11900.84 | 2913.01 | 0
13 | Project Illuminate | 2021-06-01 | 11137 | 8987.83 | 11137 | 2149.17 | 0
13 | Project Illuminate | 2021-07-01 | 11370 | 8987.83 | 11370 | 2382.17 | 0
13 | Project Illuminate | 2021-08-01 | 11140.32 | 8987.83 | 11140.32 | 2152.49 | 0
13 | Project Illuminate | 2021-09-01 | 3500.83 | 8987.83 | 8987.83 | 0 | 5487
13 | Project Illuminate | 2021-10-01 | 1987 | 8987.83 | 8987.83 | 0 | 7000.83

## 11. Magnetic Program
ID | Project Name | Month | Actual Cost | Estimate | Billing | Accrual Monthly | Actual Profit
11 | Magnetic Program | 2020-12-03 | 10000 | 20953.4 | 20953.4 | 0 | 10953.4
11 | Magnetic Program | 2021-01-03 | 14960 | 20953.4 | 20953.4 | 0 | 5993.4
11 | Magnetic Program | 2021-02-03 | 14966 | 20953.4 | 20953.4 | 0 | 5987.4
11 | Magnetic Program | 2021-03-03 | 14966 | 20953.4 | 20953.4 | 0 | 5987.4
11 | Magnetic Program | 2021-04-03 | 14966 | 20953.4 | 20953.4 | 0 | 5987.4
11 | Magnetic Program | 2021-05-03 | 14965.7 | 20953.4 | 20953.4 | 0 | 5987.7
11 | Magnetic Program | 2021-06-03 | 16960 | 20953.4 | 20953.4 | 0 | 3993.4
11 | Magnetic Program | 2021-07-03 | 14960 | 20953.4 | 20953.4 | 0 | 5993.4
11 | Magnetic Program | 2021-08-03 | 14965.57 | 20953.4 | 20953.4 | 0 | 5987.83
11 | Magnetic Program | 2021-09-03 | 14960 | 20953.4 | 20953.4 | 0 | 5993.4
11 | Magnetic Program | 2021-10-03 | 16966 | 20953.4 | 20953.4 | 0 | 3987.4
11 | Magnetic Program | 2021-11-03 | 14966 | 20953.4 | 20953.4 | 0 | 5987.4
11 | Magnetic Program | 2021-12-03 | 14966 | 20953.4 | 20953.4 | 0 | 5987.4

## 10. Project Mecha
ID | Project Name | Month | Actual Cost | Estimate | Billing | Accrual Monthly | Actual Profit
10 | Project Mecha | 2020-10-26 | 7854.32 | 11275.82 | 11275.9 | 0 | 3421.58
10 | Project Mecha | 2020-11-26 | 7854.32 | 11275.9 | 11275.9 | 0 | 3421.58
10 | Project Mecha | 2020-12-26 | 9083 | 11275.9 | 11275.9 | 0 | 2192.9
10 | Project Mecha | 2021-01-26 | 9084 | 11275.9 | 11275.9 | 0 | 2191.9
10 | Project Mecha | 2021-02-26 | 9083 | 11275.9 | 11275.9 | 0 | 2192.9
10 | Project Mecha | 2021-03-26 | 9084 | 11275.9 | 11275.9 | 0 | 2191.9
10 | Project Mecha | 2021-04-26 | 9083 | 11275.9 | 11275.9 | 0 | 2192.9
10 | Project Mecha | 2021-05-26 | 9084 | 11275.9 | 11275.9 | 0 | 2191.9
10 | Project Mecha | 2021-06-26 | 9083 | 11275.9 | 11275.9 | 0 | 2192.9
10 | Project Mecha | 2021-07-26 | 9084 | 11275.9 | 11275.9 | 0 | 2191.9
10 | Project Mecha | 2021-08-26 | 7854.21 | 11275.9 | 11275.9 | 0 | 3421.69
10 | Project Mecha | 2021-09-26 | 7854.32 | 11275.9 | 11275.9 | 0 | 3421.58

## 9. Project Systems
ID | Project Name | Month | Actual Cost | Estimate | Billing | Accrual Monthly | Actual Profit
9 | Project Systems | 2020-08-09 | 6495 | 15758.45 | 15758.45 | 0 | 9263.45
9 | Project Systems | 2020-09-09 | 11672.97 | 15758.45 | 15758.45 | 0 | 4085.48
9 | Project Systems | 2020-10-09 | 11672.97 | 15758.45 | 15758.45 | 0 | 4085.48
9 | Project Systems | 2020-11-09 | 15758.55 | 15758.45 | 15758.45 | 0 | -0.1
9 | Project Systems | 2020-12-09 | 15758.55 | 15758.55 | 15758.45 | 0 | -0.1
9 | Project Systems | 2021-01-09 | 15758.35 | 15758.55 | 15758.45 | 0 | 0.1
9 | Project Systems | 2021-02-09 | 15348.55 | 15758.55 | 15758.45 | 0 | 409.9
9 | Project Systems | 2021-03-09 | 15700.95 | 15758.55 | 15758.45 | 0 | 57.5
9 | Project Systems | 2021-04-09 | 11672.91 | 15758.55 | 15758.45 | 0 | 4085.54
9 | Project Systems | 2021-05-09 | 11672.97 | 15758.55 | 15758.45 | 0 | 4085.48
9 | Project Systems | 2021-06-09 | 11672.97 | 15758.55 | 15758.45 | 0 | 4085.48
9 | Project Systems | 2021-07-09 | 11672.97 | 15758.55 | 15758.45 | 0 | 4085.48
9 | Project Systems | 2021-08-09 | 4985 | 15758.55 | 15758.45 | 0 | 10773.45
9 | Project Systems | 2021-09-09 | 3579 | 15758.55 | 15758.45 | 0 | 12179.45

## 4. Program Pad
ID | Project Name | Month | Actual Cost | Estimate | Billing | Accrual Monthly | Actual Profit
4 | Program Pad | 2019-10-01 | 0 | 0 | 0 | 0 | 0
4 | Program Pad | 2019-11-01 | 0 | 0 | 0 | 0 | 0
4 | Program Pad | 2019-12-01 | 0 | 0 | 0 | 0 | 0
4 | Program Pad | 2020-01-01 | 0 | 0 | 0 | 0 | 0
4 | Program Pad | 2020-02-01 | 0 | 0 | 0 | 0 | 0
4 | Program Pad | 2020-03-01 | 0 | 0 | 0 | 0 | 0
4 | Program Pad | 2020-04-01 | 7056.23 | 13421.92 | 13421.92 | 0 | 6365.69
4 | Program Pad | 2020-05-01 | 8695.12 | 13421.92 | 13421.92 | 0 | 4726.8
4 | Program Pad | 2020-06-01 | 9235.56 | 13421.92 | 13421.92 | 0 | 4186.36
4 | Program Pad | 2020-07-01 | 9586.53 | 13421.92 | 13421.92 | 0 | 3835.39
4 | Program Pad | 2020-08-01 | 9968.36 | 13421.92 | 13421.92 | 0 | 3453.56
4 | Program Pad | 2020-09-01 | 10235.69 | 13421.92 | 13421.92 | 0 | 3186.23
4 | Program Pad | 2020-10-01 | 10962.36 | 13421.92 | 13421.92 | 0 | 2459.56
4 | Program Pad | 2020-11-01 | 11068.36 | 13421.92 | 13421.92 | 0 | 2353.56
4 | Program Pad | 2020-12-01 | 11675 | 13421.92 | 13421.92 | 0 | 1746.92
4 | Program Pad | 2021-01-01 | 11235.36 | 13421.92 | 13421.92 | 0 | 2186.56
4 | Program Pad | 2021-02-01 | 10992.36 | 13421.92 | 13421.92 | 0 | 2429.56
4 | Program Pad | 2021-03-01 | 10568.56 | 13421.92 | 13421.92 | 0 | 2853.36
4 | Program Pad | 2021-04-01 | 10001.35 | 13421.92 | 13421.92 | 0 | 3420.57
4 | Program Pad | 2021-05-01 | 9668.36 | 13421.92 | 13421.92 | 0 | 3753.56
4 | Program Pad | 2021-06-01 | 9273.25 | 13421.92 | 13421.92 | 0 | 4148.67
4 | Program Pad | 2021-07-01 | 9156.36 | 13421.92 | 13421.92 | 0 | 4265.56
4 | Program Pad | 2021-08-01 | 8965.36 | 13421.92 | 13421.92 | 0 | 4456.56
4 | Program Pad | 2021-09-01 | 8002.23 | 13421.92 | 13421.92 | 0 | 5419.69
4 | Program Pad | 2021-10-01 | 0 | 0 | 0 | 0 | 0
4 | Program Pad | 2021-11-01 | 0 | 0 | 0 | 0 | 0
4 | Program Pad | 2021-12-01 | 0 | 0 | 0 | 0 | 0

## 8. Command Program
ID | Project Name | Month | Actual Cost | Estimate | Billing | Accrual Monthly | Actual Profit
8 | Command Program | 2019-10-01 | 0 | 0 | 0 | 0 | 0
8 | Command Program | 2019-11-01 | 0 | 0 | 0 | 0 | 0
8 | Command Program | 2019-12-01 | 0 | 0 | 0 | 0 | 0
8 | Command Program | 2020-01-01 | 0 | 0 | 0 | 0 | 0
8 | Command Program | 2020-02-01 | 0 | 0 | 0 | 0 | 0
8 | Command Program | 2020-03-01 | 0 | 0 | 0 | 0 | 0
8 | Command Program | 2020-04-01 | 0 | 0 | 0 | 0 | 0
8 | Command Program | 2020-05-01 | 0 | 0 | 0 | 0 | 0
8 | Command Program | 2020-06-01 | 0 | 0 | 0 | 0 | 0
8 | Command Program | 2020-07-01 | 4504.13 | 6706.14 | 6706.14 | 0 | 2202.01
8 | Command Program | 2020-08-01 | 5216.35 | 6706.14 | 6706.14 | 0 | 1489.79
8 | Command Program | 2020-09-01 | 5325.65 | 6706.14 | 6706.14 | 0 | 1380.49
8 | Command Program | 2020-10-01 | 6029.21 | 6706.14 | 7733.14 | 1027 | 1703.93
8 | Command Program | 2020-11-01 | 5809.56 | 6706.14 | 7006.14 | 300 | 1196.58
8 | Command Program | 2020-12-01 | 5798.65 | 6706.14 | 6906.14 | 200 | 1107.49
8 | Command Program | 2021-01-01 | 4683.56 | 6706.14 | 6706.14 | 0 | 2022.58
8 | Command Program | 2021-02-01 | 4299.98 | 6706.14 | 6706.14 | 0 | 2406.16
8 | Command Program | 2021-03-01 | 4056.58 | 6706.14 | 6706.14 | 0 | 2649.56
8 | Command Program | 2021-04-01 | 0 | 0 | 0 | 0 | 0
8 | Command Program | 2021-05-01 | 0 | 0 | 0 | 0 | 0
8 | Command Program | 2021-06-01 | 0 | 0 | 0 | 0 | 0
8 | Command Program | 2021-07-01 | 0 | 0 | 0 | 0 | 0
8 | Command Program | 2021-08-01 | 0 | 0 | 0 | 0 | 0
8 | Command Program | 2021-09-01 | 0 | 0 | 0 | 0 | 0
8 | Command Program | 2021-10-01 | 0 | 0 | 0 | 0 | 0
8 | Command Program | 2021-11-01 | 0 | 0 | 0 | 0 | 0
8 | Command Program | 2021-12-01 | 0 | 0 | 0 | 0 | 0

## 12. Project Zen
ID | Project Name | Month | Actual Cost | Estimate | Billing | Accrual Monthly | Actual Profit
12 | Project Zen | 2019-10-01 | 0 | 0 | 0 | 0 | 0
12 | Project Zen | 2019-11-01 | 0 | 0 | 0 | 0 | 0
12 | Project Zen | 2019-12-01 | 0 | 0 | 0 | 0 | 0
12 | Project Zen | 2020-01-01 | 0 | 0 | 0 | 0 | 0
12 | Project Zen | 2020-02-01 | 0 | 0 | 0 | 0 | 0
12 | Project Zen | 2020-03-01 | 0 | 0 | 0 | 0 | 0
12 | Project Zen | 2020-04-01 | 0 | 0 | 0 | 0 | 0
12 | Project Zen | 2020-05-01 | 0 | 0 | 0 | 0 | 0
12 | Project Zen | 2020-06-01 | 0 | 0 | 0 | 0 | 0
12 | Project Zen | 2020-07-01 | 0 | 0 | 0 | 0 | 0
12 | Project Zen | 2020-08-01 | 0 | 0 | 0 | 0 | 0
12 | Project Zen | 2020-09-01 | 0 | 0 | 0 | 0 | 0
12 | Project Zen | 2020-10-01 | 0 | 0 | 0 | 0 | 0
12 | Project Zen | 2020-11-01 | 0 | 0 | 0 | 0 | 0
12 | Project Zen | 2020-12-01 | 3908.23 | 6319.15 | 6319.15 | 0 | 2410.92
12 | Project Zen | 2021-01-01 | 4482.02 | 6319.15 | 6319.15 | 0 | 1837.13
12 | Project Zen | 2021-02-01 | 5023.56 | 6319.15 | 6319.15 | 0 | 1295.59
12 | Project Zen | 2021-03-01 | 4925.23 | 6319.15 | 6319.15 | 0 | 1393.92
12 | Project Zen | 2021-04-01 | 4637.95 | 6319.15 | 6319.15 | 0 | 1681.2
12 | Project Zen | 2021-05-01 | 3913.01 | 6319.15 | 6319.15 | 0 | 2406.14
12 | Project Zen | 2021-06-01 | 0 | 0 | 0 | 0 | 0
12 | Project Zen | 2021-07-01 | 0 | 0 | 0 | 0 | 0
12 | Project Zen | 2021-08-01 | 0 | 0 | 0 | 0 | 0
12 | Project Zen | 2021-09-01 | 0 | 0 | 0 | 0 | 0
12 | Project Zen | 2021-10-01 | 0 | 0 | 0 | 0 | 0
12 | Project Zen | 2021-11-01 | 0 | 0 | 0 | 0 | 0
12 | Project Zen | 2021-12-01 | 0 | 0 | 0 | 0 | 0

## 14. Project Synergy
ID | Project Name | Month | Actual Cost | Estimate | Billing | Accrual Monthly | Actual Profit
14 | Prject Synergy | 2019-10-01 | 0 | 0 | 0 | 0 | 0
14 | Prject Synergy | 2019-11-01 | 0 | 0 | 0 | 0 | 0
14 | Prject Synergy | 2019-12-01 | 0 | 0 | 0 | 0 | 0
14 | Prject Synergy | 2020-01-01 | 0 | 0 | 0 | 0 | 0
14 | Prject Synergy | 2020-02-01 | 0 | 0 | 0 | 0 | 0
14 | Prject Synergy | 2020-03-01 | 0 | 0 | 0 | 0 | 0
14 | Prject Synergy | 2020-04-01 | 0 | 0 | 0 | 0 | 0
14 | Prject Synergy | 2020-05-01 | 0 | 0 | 0 | 0 | 0
14 | Prject Synergy | 2020-06-01 | 0 | 0 | 0 | 0 | 0
14 | Prject Synergy | 2020-07-01 | 0 | 0 | 0 | 0 | 0
14 | Prject Synergy | 2020-08-01 | 0 | 0 | 0 | 0 | 0
14 | Prject Synergy | 2020-09-01 | 0 | 0 | 0 | 0 | 0
14 | Prject Synergy | 2020-10-01 | 0 | 0 | 0 | 0 | 0
14 | Prject Synergy | 2020-11-01 | 0 | 0 | 0 | 0 | 0
14 | Prject Synergy | 2020-12-01 | 0 | 0 | 0 | 0 | 0
14 | Prject Synergy | 2021-01-01 | 0 | 0 | 0 | 0 | 0
14 | Prject Synergy | 2021-02-01 | 5023.56 | 7870.77 | 7870.77 | 0 | 2847.21
14 | Prject Synergy | 2021-03-01 | 5689.63 | 7870.77 | 7870.77 | 0 | 2181.14
14 | Prject Synergy | 2021-04-01 | 6137.95 | 7870.77 | 7870.77 | 0 | 1732.82
14 | Prject Synergy | 2021-05-01 | 6486.32 | 7870.77 | 7870.77 | 0 | 1384.45
14 | Prject Synergy | 2021-06-01 | 6656.56 | 7870.77 | 7870.77 | 0 | 1214.21
14 | Prject Synergy | 2021-07-01 | 6652.36 | 7870.77 | 7870.77 | 0 | 1218.41
14 | Prject Synergy | 2021-08-01 | 6089.35 | 7870.77 | 7870.77 | 0 | 1781.42
14 | Prject Synergy | 2021-09-01 | 5689.56 | 7870.77 | 7870.77 | 0 | 2181.21
14 | Prject Synergy | 2021-10-01 | 4438.11 | 7870.77 | 7870.77 | 0 | 3432.66
14 | Prject Synergy | 2021-11-01 | 0 | 0 | 0 | 0 | 0
14 | Prject Synergy | 2021-12-01 | 0 | 0 | 0 | 0 | 0

## 5. Project Breeze
ID | Project Name | Month | Actual Cost | Estimate | Billing | Accrual Monthly | Actual Profit
5 | Project Breeze | 2019-10-01 | 0 | 0 | 0 | 0 | 0
5 | Project Breeze | 2019-11-01 | 0 | 0 | 0 | 0 | 0
5 | Project Breeze | 2019-12-01 | 0 | 0 | 0 | 0 | 0
5 | Project Breeze | 2020-01-01 | 0 | 0 | 0 | 0 | 0
5 | Project Breeze | 2020-02-01 | 0 | 0 | 0 | 0 | 0
5 | Project Breeze | 2020-03-01 | 0 | 0 | 0 | 0 | 0
5 | Project Breeze | 2020-04-01 | 3898.36 | 5463.71 | 5463.71 | 0 | 1565.35
5 | Project Breeze | 2020-05-01 | 4086.65 | 5463.71 | 5463.71 | 0 | 1377.06
5 | Project Breeze | 2020-06-01 | 4269.36 | 5463.71 | 5463.71 | 0 | 1194.35
5 | Project Breeze | 2020-07-01 | 4696.36 | 5463.71 | 5463.71 | 0 | 767.35
5 | Project Breeze | 2020-08-01 | 4723.25 | 5463.71 | 5463.71 | 0 | 740.46
5 | Project Breeze | 2020-09-01 | 4102.32 | 5463.71 | 5463.71 | 0 | 1361.39
5 | Project Breeze | 2020-10-01 | 3925.36 | 5463.71 | 5463.71 | 0 | 1538.35
5 | Project Breeze | 2020-11-01 | 3921.14 | 5463.71 | 5463.71 | 0 | 1542.56
5 | Project Breeze | 2020-12-01 | 0 | 0 | 0 | 0 | 0
5 | Project Breeze | 2021-01-01 | 0 | 0 | 0 | 0 | 0
5 | Project Breeze | 2021-02-01 | 0 | 0 | 0 | 0 | 0
5 | Project Breeze | 2021-03-01 | 0 | 0 | 0 | 0 | 0
5 | Project Breeze | 2021-04-01 | 0 | 0 | 0 | 0 | 0
5 | Project Breeze | 2021-05-01 | 0 | 0 | 0 | 0 | 0
5 | Project Breeze | 2021-06-01 | 0 | 0 | 0 | 0 | 0
5 | Project Breeze | 2021-07-01 | 0 | 0 | 0 | 0 | 0
5 | Project Breeze | 2021-08-01 | 0 | 0 | 0 | 0 | 0
5 | Project Breeze | 2021-09-01 | 0 | 0 | 0 | 0 | 0
5 | Project Breeze | 2021-10-01 | 0 | 0 | 0 | 0 | 0
5 | Project Breeze | 2021-11-01 | 0 | 0 | 0 | 0 | 0
5 | Project Breeze | 2021-12-01 | 0 | 0 | 0 | 0 | 0

## 15. Native Program
ID | Project Name | Month | Actual Cost | Estimate | Billing | Accrual Monthly | Actual Profit
15 | Native Program | 2019-10-01 | 0 | 0 | 0 | 0 | 0
15 | Native Program | 2019-11-01 | 0 | 0 | 0 | 0 | 0
15 | Native Program | 2019-12-01 | 0 | 0 | 0 | 0 | 0
15 | Native Program | 2020-01-01 | 0 | 0 | 0 | 0 | 0
15 | Native Program | 2020-02-01 | 0 | 0 | 0 | 0 | 0
15 | Native Program | 2020-03-01 | 0 | 0 | 0 | 0 | 0
15 | Native Program | 2020-04-01 | 0 | 0 | 0 | 0 | 0
15 | Native Program | 2020-05-01 | 0 | 0 | 0 | 0 | 0
15 | Native Program | 2020-06-01 | 0 | 0 | 0 | 0 | 0
15 | Native Program | 2020-07-01 | 0 | 0 | 0 | 0 | 0
15 | Native Program | 2020-08-01 | 0 | 0 | 0 | 0 | 0
15 | Native Program | 2020-09-01 | 0 | 0 | 0 | 0 | 0
15 | Native Program | 2020-10-01 | 0 | 0 | 0 | 0 | 0
15 | Native Program | 2020-11-01 | 0 | 0 | 0 | 0 | 0
15 | Native Program | 2020-12-01 | 0 | 0 | 0 | 0 | 0
15 | Native Program | 2021-01-01 | 0 | 0 | 0 | 0 | 0
15 | Native Program | 2021-02-01 | 0 | 0 | 0 | 0 | 0
15 | Native Program | 2021-03-01 | 8568.36 | 13198.95 | 13198.95 | 0 | 4630.59
15 | Native Program | 2021-04-01 | 9036.56 | 13198.95 | 13198.95 | 0 | 4162.39
15 | Native Program | 2021-05-01 | 10006.56 | 13198.95 | 13198.95 | 0 | 3192.39
15 | Native Program | 2021-06-01 | 10158.36 | 13198.95 | 13198.95 | 0 | 3040.59
15 | Native Program | 2021-07-01 | 11668.56 | 13198.95 | 13198.95 | 0 | 1530.39
15 | Native Program | 2021-08-01 | 10889.36 | 13198.95 | 13198.95 | 0 | 2309.59
15 | Native Program | 2021-09-01 | 9936.3 | 13198.95 | 13198.95 | 0 | 3262.65
15 | Native Program | 2021-10-01 | 9025.56 | 13198.95 | 13198.95 | 0 | 4173.39
15 | Native Program | 2021-11-01 | 8056.36 | 13198.95 | 13198.95 | 0 | 5142.59
15 | Native Program | 2021-12-01 | 0 | 0 | 0 | 0 | 0

## Sheet2 (hidden)
Pricing Model | Portfolio | ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Project Bid Value | Total Cost | Profit | Profit %
Fixed Price | IMS | 1 | Project Breeze | 2020-04-19 08:00 | 2020-12-19 17:00 | 8m |  | 0 | 4000 | 0 | 43709.64 | 33622.8 | 10086.84 | 30%
Fixed Price | Client Based | 23 | Command Program | 2020-07-11 | 2021-04-11 17:00 | 9m |  | 0 | 2000 | 0 | 60355.2444 | 45723.67 | 14631.5744 | 32%
T & M | Client Based | 24 | Project Point | 2020-05-05 08:00 | 2021-06-05 17:00 | 13m |  | 0 | 1000 | 0 | 91000 | 176564.43 | -85564.43 | -48.46%
Fixed Price | IMS | 1 | Project Mecha | 2020-10-26 08:00 | 2021-09-26 17:00 | 11m | Analyst programmer;IT Manager[0.20 #1] | 595.2 | 0 | 0 | 135310.721 | 104085.17 | 31225.551 | 30%
Fixed Price | R & D | 39 | Program Pad | 2020-04-01 08:00 | 2021-10-01 17:00 | 18m | Marketing manager[0.50 #1];IT Manager[0.10 #1] | 286.4 | 10000 | 0 | 241594.568 | 176346.4 | 65248.168 | 37%
Fixed Price | Client Based | 40 | Project Synergy | 2021-02-12 08:00 | 2021-11-12 17:00 | 9m | IT Manager[0.10 #1];Marketing manager[0.50 #1] | 286.4 | 3000 | 0 | 70836.956 | 52863.4 | 17973.556 | 34%
Fixed Price | Client Based | 2 | Dynamic Program | 2020-03-01 08:00 | 2021-05-01 16:00 | 14m | Analyst programmer | 133 | 0 | 0 | 130653.4411 | 98235.67 | 32417.7711 | 33%
Fixed Price | R & D | 3 | Project Zen | 2020-12-17 08:00 | 2021-06-17 17:00 | 6m | Analyst programmer | 152 | 0 | 0 | 37914.9 | 26890 | 11024.9 | 41%
Fixed Price | IMS | 4 | Project Illuminate | 2021-01-02 08:00 | 2021-10-02 12:00 | 10m | Database administrator | 76 | 0 | 0 | 89878.329 | 66576.54 | 23301.789 | 35%
Fixed Price | Client Based | 5 | Magnetic Program | 2020-12-03 13:00 | 2021-12-03 14:00 | 12m | Analyst programmer[0.50 #1];Database administrator[0.50 #1] | 19 | 0 | 0 | 272394.248 | 194567.32 | 77826.928 | 40%
Fixed Price | Client Based | 6 | Project Systems | 2020-08-09 14:00 | 2021-09-09 16:00 | 13m | Database administrator | 38 | 0 | 0 | 220619.3085 | 163421.71 | 57197.5985 | 35%
Fixed Price | Client Based | 7 | Native Program | 2021-03-07 08:00 | 2021-12-07 17:00 | 9m | Analyst programmer[0.30 #1] | 91.2 | 0 | 0 | 118790.5328 | 87345.98 | 31444.5528 | 36%
Fixed Price | R & D | 8 | Project Force | 2020-06-02 16:00 | 2021-09-02 14:00 | 15m | Database administrator | 114 | 0 | 0 | 246512.6006 | 185347.82 | 61164.7806 | 33%
Fixed Price | Client Based | 9 | Quest Program | 2019-12-05 16:00 | 2021-07-05 16:00 | 19m | Database administrator | 152 | 0 | 0 | 338729.9666 | 238542.23 | 100187.7366 | 42%
Fixed Price | IMS | 10 | Project Signal | 2019-10-06 08:00 | 2021-03-06 17:00 | 17m | Programmers | 272 | 0 | 0 | 272502.4038 | 197465.51 | 75036.8938 | 38%
[5 empty] | Cost | Billing | Accrual
|  |  | Month | Resource
|  |  |  | Assets | Cloud
On premise
Resource Cost
|  |  | Name |  |  | Jan | [8 empty] | Nov | Dec
[6 empty] | Individual Cost | Billing Individual | Accrual Individual | Total Cost | Total Billing | Accrual Monthly | Profit
|  |  | Project Breeze | PMO Resources | IT Manager
Analyst programmer
Database administrator
Programmers
Marketing manager
|  |  |  | Assets | Cloud Based
On Premise
|  |  | Command Program | PMO Resources | IT Manager
Analyst programmer
Database administrator
Programmers
Marketing manager
|  |  |  | Assets | Cloud Based
On Premise
[5 empty] | Stages | Initiation
|  |  | Project Point |  |  | Execution
Closure
Project Mecha
Program Pad
Project Synergy
Dynamic Program
Project Zen
Project Illuminate
Magnetic Program
Project Systems
Native Program
Project Force
Quest Program
Project Signal

## Resources (hidden)
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Programmers | Renewable | 3 Programmers | 0 | 17 | 10;11[1.50 Programmers];16[2.00 Programmers];17[2.50 Programmers];18[2.00 Programmers];19[3.00 Programmers];20[2.00 Programmers];21[3.00 Programmers];31[2.00 Programmers];32; | 4845
2 | IT Manager | Renewable | 1 IT Manager | 0 | 29 | 1[0.20 IT Manager];39[0.10 IT Manager];40[0.10 IT Manager];28;29[0.50 IT Manager];34;35[0.50 IT Manager]; | 493
3 | Database administrator | Renewable | 1 Database administrator | 0 | 19 | 4;5[0.50 Database administrator];6;8;9;12[0.40 Database administrator];13[0.60 Database administrator];14[0.40 Database administrator];15[0.60 Database administrator];31[0.30 Database administrator]; | 1103.9
4 | Analyst programmer | Renewable | 1 Analyst programmer | 0 | 19 | 1;2;3;5[0.50 Analyst programmer];7[0.30 Analyst programmer];27[0.30 Analyst programmer];28;31[0.10 Analyst programmer];33[0.20 Analyst programmer];34; | 1084.9
5 | Secretary | Renewable | 1 Secretary | 0 | 11 | 37;27;33; | 286
6 | Marketing manager | Renewable | 1 Marketing manager | 0 | 30 | 39[0.50 Marketing manager];40[0.50 Marketing manager];37[0.50 Marketing manager]; | 510
7 | Sales representatives | Renewable | 2 Sales representatives | 0 | 15 | 38[2.00 Sales representatives]; | 2400
8 | Technicians | Renewable | 3 Technicians | 0 | 13 | 36[3.00 Technicians];41;42; | 2600

## Risk Analysis (hidden)
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Commercial IT Project | 453h |  |  |  |  | 99 | 100 | 101
22 | Explore the market | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
23 | Set up a survey | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
24 | Analysis of the market | 120h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
1 | Problem study/analysis | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
39 | Negotiate and buy server | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
40 | Negotiate and buy computer | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
2 | Processmodels (BPMN) | 7h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
3 | Conceptual datamodel (ER) | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
4 | Normalisation DB | 4h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
5 | Datamap | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
6 | Logic Databasemodel | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
7 | Software design (UML-class diagram) | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
8 | Develop Database Tables 1 | 6h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
9 | Develop Database Tables 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
10 | Design & Develop GUI 1 | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
11 | Design & Develop GUI 2 | 21h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
25 | Design CD-box | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
26 | Design CD-labels | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
12 | Develop SQL's 1 | 18h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
13 | Develop SQL's 2 | 20h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
14 | Debug SQL’s 1 | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
15 | Debug SQL’s 2 | 12h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
16 | Implement SQL’s in JAVA 1 | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
17 | Implement SQL’s in JAVA 2 | 1h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
18 | Develop program 1 | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
19 | Develop program 2 | 29h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
20 | Testing & Debugging 1 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
21 | Testing & Debugging 2 | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
38 | Visitations by sales representatives | 80h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
37 | Direct mailings | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
27 | Make up report + presentation Alpha version | 16h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
28 | Presentation Alpha version | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
29 | Reading of management report + Approval Alpha | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
31 | Testing phase Alpha version | 24h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
32 | Fix outstanding problems from Alpha | 10h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
33 | Make up Report+ presentation Beta version | 8h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
34 | Presentation Beta version | 2h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
35 | Reading of management report + Approval Beta | 5h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
36 | Launch and installation Beta version | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
41 | Installation server | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120
42 | Installation computer | 40h | standard - symmetric | 80 | 100 | 120 | 80 | 100 | 120

## Agenda (hidden)
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview (hidden)
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold